## Sheet1
Care Bundle Project Tracker
1) Preparation |  |  | 2) Launch |  |  | 3) Diagnosis |  |  | 4) Implementation |  |  | 5) Evaluation
| Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
1 | Core team Identified | Amber | 7 | Set up on BTS System | Amber | 10 | Process Mapping | Amber | 14 | Agree New Pathway | Amber | 20 | Improvements Validated | Amber
2 | Wider Team Engaged | Amber | 8 | Data Collection Plan | Amber | 11 | Root Cause Analysis | Amber | 15 | Action Plan | Amber | 21 | Initial Learning and Lessons | Amber
3 | Project Definition | Amber | 9 | Peer Support | Amber | 12 | Case Note Audit | Amber | 16 | PDSA | Amber | 22 | Project Closure | Amber
4 | Project Plan and Timeline | Amber |  | Showcase work | Amber | 13 | Demand and Capacity | Amber | 17 | Compliance | Amber |  | Showcase work | Amber
5 | Communication Plan | Amber |  |  | Amber |  | Showcase work | Amber | 18 | Project plan update | Amber |  |  | Amber
6 | Patient and Carer Engagement | Amber |  |  | Amber |  |  | Amber | 19 | Improvements Recorded | Amber |  |  | Amber
| Showcase work | Amber |  |  | Amber |  |  | Amber |  | Showcase work | Amber |  |  | Amber
|  | Amber |  |  | Amber |  |  | Amber |  |  | Amber |  |  | Amber
|  | Amber |  |  | Amber |  |  | Amber |  |  | Amber |  |  | Amber
| PREPARATION PHASE |  |  | LAUNCH PHASE |  |  | DIAGNOSIS PHASE |  |  | IMPLEMENTATION PHASE |  |  | EVALUATION PHASE
1) | Core team identified: |  | 7) | Set up on BTS System |  | 10) | Process Mapping |  | 14) | Agree New Pathway: |  | 20) | Improvements Validated:
| Clinical Lead |  |  | Appropriate users registered |  |  | Date and Venue Agreed |  |  | Map created and agreed |  |  | PDSA cycles evaluated
| Managerial Lead | [5 empty] | Facilitator identified |  |  | Identify improvement opportunities |  |  | Final data analysis
| Remainder of Core team representing all roles in the pathway |  | 8) | Data Collection Plan: |  |  | Agreed who should attend | [5 empty] | Data Validated
| Core team committed to time out / protected time out |  |  | Agreed who will be responsible for collecting the data |  |  | Defined Scope |  | 15) | Action Plan: |  |  | Objectives met?
|  |  |  | Agreed who will be responsible for imputting the data |  |  | Map Completed |  |  | Just do its' documented
2) | Wider Team Engagement: |  |  | Agree internal dissemination of data |  |  | Map validated by data |  |  | Timescales included on plans |  | 21) | Initial Learning and Lessons:
| Executive Sponsor | [5 empty] | Validated by walking the pathway |  |  | Priorities highlighted |  |  | Learning identified
| IT / Clinical Audit |  | 9) | Peer Support |  |  | Any low level mapping required? |  |  | Who what when where agreed |  |  | Captured and recorded
| Communication Department |  |  | Identify team representation for Webex calls |  |  | Any area not mapped? |  |  | Completed? |  |  | Shared?
| Data Analyst |  |  | Agree communication mechanism with other sites |  |  | Analysis of map undertaken?
| Met with Chief Executive | [5 empty] | Issues / Solutions/ Challenges / Actions / PDSA / identified |  | 16) | PDSA |  | 22) | Project Closure:
[10 empty] | PDSA cycles identified |  |  | Case Studies
3) | Project definition: |  |  |  |  | 11) | Root Cause Analysis: |  |  | PDSA learning identified |  |  | Publications
| National Objectives Clear to Whole Team | [5 empty] | Analysis of process mapping completed | [5 empty] | Final report
| Baseline (Yearly) data collected and submitted | [5 empty] | Problems quantified and prioritised |  | 17) | Compliance |  |  | Sign off and closure meeting with Team
| Baseline (Yearly) data analysed and understood | [5 empty] | Deeper cause(s) interpreted correctly (e.g. 5-whys, Fishbone) |  |  | Actions taken to ensure all patients receive care bundle |  |  | Sign off and closure meeting with Exec Sponsor
| Project scope clearly defined and agreed | [8 empty] | Actions taken to ensure all care bundles complete |  |  | Everything recorded and written up
[6 empty] | 12) | Case Note Audit: | [5 empty] | Evaluation of Project, team and process
4) | Project Plan & Timeline: | [5 empty] | Audit of care bundle items - CAP |  | 18) | Project Plan Updated
| Key project phases, milestones & realistic timeframes documented | [5 empty] | Audit of care bundle items - Acute COPD |  |  | Updated including timescales, who, what, where, when
| Risk and escalation plan documented | [5 empty] | Audit of care bundle items - COPD Discharge
| Project team time identified and agreed | [7 empty] | 19) | Improvements Recorded
| NHS Improvement tool access and usage agreed |  |  |  |  | 13) | Demand and Capacity |  |  | Ongoing audit of care bundle compliance
[7 empty] | Is this tool appropriate? |  |  | Monthly data collection
5) | Communication Plan: | [5 empty] | Is the data available? |  |  | LTC6 Data collection
| Communication plan documented | [5 empty] | Who, What, Where, When has been agreed
| List of who should be communicated to including key stakeholders | [5 empty] | Analysis complete
| Frequency of communication agreed | [5 empty] | Actions / plan agreed
Agreed how the information will be communicated
Who will receive relevant progress reports
6) | Patient and Carer Engagement:
Agree method for implementation of LTC6
Identify team member who will lead on this
v2 October 2016